## Sheet1
Category | Item | Description | Comments | Putative Difficulty | Relevant Target Dates | Coordination
Scanning | Scan using new machine | Use the new computer for scanning |  | small | April Garberville election. | It would be good to have a few sample ballots to test scanning.
Scanning | Reliable backup to external drive | Backup program that ensures that every image is properly backed up without requiring the operator to enter anything. | Leaves images in JPG format rather than using more advanced compression. | medium
Scanning | Signed image file | Configure our computer at Elections to create a set of signed images suitable for creating DVD. Run immediately after scanning. | File should be available within a few hours of scanning the last ballot. | small
Scanning | Verify scanning computer date and time. | On each reboot have the operator verify the date and time. | Because our computer is not on the network its time drifts from the actual time. This just reminds people to verify and/or reset it. | small
Scanning | Run two scanners. | Develop a UI that allows an operator to run two scanners simultaneously. |  | medium-large | 2018 mid-term elections | Might require replacing the consumables in the old scanner. Requires some choreogrpahy among the volunteers to keep the operator supplied with prepared batches.
Scanning | Batch header sheets | Instead of having user type in batch control information pick it up from a batch header sheet. This would reduce the interbatch time. | A header sheet would have be preprinted with "check boxes" to identify precinct, date and time of scanning and the expected count. Volunteers preparing the batch would fill out the sheet and add it to the front. Document would be scanned to capture the operator and preparer's initials as images and the documents would be retained with ballot images. | medium |  | Requires workflow changes.
Scanning | Count ballots by precinct while scanning. | Running total of ballots (but not counts) as scanning occurs. |  | medium
Scanning | GUI Control over scanning | Fix issues with current GUI-controlled scanning. |  | medium
Ballot Analysis | Fine tuning ballot analysis | Review and possibly enhance deskewing. |  | medium
Ballot Analysis | Fine tuning ballot analysis | Review and possibly enhance decision roles with respect to whether a choice was voted. |  | small - medium
Ballot Analysis | "unanalyzable" ballots, part 1 | Establish a procedure for dealing with ballots that the analysis routine does not accept. Probably manual touchup of the image. | The chosen approach would need to include a way of documenting what was done, and by whom. The approach used for email and physically damaged ballots looks good. | small |  | The chosen approach would need to be vetted with the ETP group before implementation.
Ballot Analysis | "unanalyzable" ballots, part 2 | Where unanalyzable ballots are found, attempt improvements to analysis to make them analyzable. |  | ?
Housekeeping | Create a GIT project and a dependency map. | Items necessary to ensure Wes can support the process. | If we were to be approached about using the software, this would be valuable then, too. | small
Housekeeping | Attempt to get scanning on a more recent version of Ubunti | Items necessary to ensure Wes can support the process. | Ubuntu 12.04 reached "end of life" this year, 5 years after its official release. This is not a huge deal, but it makes it more difficult to get third-party support on all the software we use. | ?
Housekeeping | Attempt to get analysis on a more recent version of Ubunti | Items necessary to ensure Wes can support the process. | Ubuntu 12.04 reached "end of life" this year, 5 years after its official release. This is not a huge deal, but it makes it more difficult to get third-party support on all the software we use. | ?
Ballot Analysis | Improvements in template building | Use prepared files for mapping bar codes to precinct identifiers. |  | medium
Ballot Analysis | Improvements in template building | Use prepared files of text of contests and choices in order. | Get file from Elections ahead of the election or have volunteers prepare and review it. If the latter, use an on-line approach. | medium
Ballot Analysis | Improvements in template building | Precreate templates from official PDFs | Get PDFs from Elections ahead of the election and have templates ready to go before scanning ballots. | small |  | Requires access to the PDFs.
Ballot Analysis | Volunteer adjudication of overvoted or apparently unvoted ballots. | Establish a UI that displays the relevant portions of a ballot page requiring human review and accepts their interpretation. | Ideally on-line, but requires some kind of login. Multiple volunteers per item? Requires logging of who adjudicated what. | large
Scanning/ Ballot Analysis | Near real-time vote counting | Establish a scoreboard that shows the running totals for choices, contests (and precincts?) | In order to ensure the scanning runs as fast as possible, this would run somewhat behind the scanning. This may be feasible if we have completed the template improvements. | medium
Reporting | Reports of our results on ETP web site. | Establish a report format in terms of the size of our discrepancy vs the vote margins. | Go back to include November and March ballots? | small |  | Report format and each posted instance requires the review of ETP members.
Reporting | Map outputs to geographical coordinates for fancy reports. | Allow people to view the vote density on a particular contest and choice on a map of Humboldt county. | http://www.humboldtgov.org/1357/Web-GIS apparently has geomapping information for election precints. | medium?
Reporting | Additional information | Include additional information in reports such as the dates of scanning, the initials of those present during the scanning and the location (which is a given) |  | medium |  | Requires workflow changes to capture "those present" and, presumably, to assign names to user initials.